## Slide 1: Digital Assistance 1.0 Proposal for FedEx

## Slide 2: Contents
Chart: 
Executive Summary | 3
Scope | 4
Timeline | 6
High Level Solution Map | 7
Resource Plan | 8
Effort Estimates and Fees | 9
Assumptions | 10

## Slide 3: Executive Summary
Chart: 
FedEx Corporate Business Services (CBS) implemented Oracle Cloud for FedEx Supply Chain (FSC) OpCo and has undertaken an initiative (“Novita”) to expand the Oracle Cloud solution for global Enterprise with initial deployment to the Express International.
The FedEx CBS team is evaluating current Oracle Cloud Operate (support) model to build upon existing service level quality while increasing automation, standardization and scaling the service model for global organization through a dedicated cross-functional support team.
The overall value proposition is to increase customer satisfaction, lower operating costs, while reallocating business resources to work on prioritized CBS projects. Deploying Digital Assistants is a key component to achieve these goals. This document provides the details about the first step/Release 1.0 of this Digital Assistance workforce journey.

## Slide 4: Scope
Chart: 
Application | Module | Use Cases
Enwisen Ticketing Tool | NA | Query ticket User will provide information like ticket priority or ticket description or can reassign the ticket to different user in ticketing system Status of specific ticket by providing the ticket number Number of tickets assigned to a user with its status ( i.e. Number of open tickets = 10, Number of closed tickets = 20) Number of tickets which are open from last 2 weeks. Aging report on tickets Number of tickets that are closed yesterday or today or on specific date Report of tickets created from yesterday or created from last 1 week ETA for specific ticket
Oracle SaaS Cloud | Order Management | ADS Orders past due for a particular location Sales orders that are past due to "Memphis" location, how many are Picked, how many are shipped? GPS Orders in Error All orders, past due, having source order number starting from “RC”. From these orders how many are in error?
Oracle SaaS Procurement | Self-service Procurement | Expense Requisitions Status of all the catalog requisitions generated today Requisitions awaiting approval Requisitions created by the requestor <xxxx> Automatic PO for approved Requisitions Expense requisitions created today. Out of those, how many are requisitions are approved ? Purchase Orders generated for these approved requisitions
We have considered the following scope for Release 1.0, which will be primarily focused on query based use cases.
We will work end-users to confirm these use cases.

## Slide 5
Chart: 
Application | Module | Use Cases | Count
Oracle SaaS Cloud | Inventory Management | 1. What is the On-Hand quantity available for Item <xxx> in Organization <xxx> ? 2. What are the OEM PO receipts happened today ? Org = ADS, Subinvetory = ACPK. 3. How many new ADS Items are created in last x days ? 4. How many new AVR Items are created in last x days ? 5. What are the Direct-Org transfers happened today from ADS to AVR Org ? | 5
Oracle SaaS Cloud | Accounts Payables | Rejected Invoice 1. What is the approval status of invoice <xxxx>? 2. Who rejected the invoice <xxxx>? Invoice Pending Approval 3. What is the approval status of invoice <xxxx>? 4. List name of the employess with whom invoice approval is pending? Invoice Payment 5. Is invoice <xxxx> paid? 6. When was the payment done? Expense 7. What is the status of my Expense report 8. Creating expense reports | 8
Oracle SaaS Cloud | Account Receivables | Receivable Invoice 1. Does AR invoice <XXXX> present in Receivables? 2. What is the invoice amount? Receivable Invocie Payment 3. Are there any adjustment made on invoice <xxxx>? 4. Are the adjustments approved?Receipt Application 5. Is invoice <xxxx> paid? 6. What is the receipt number? | 6
Oracle SaaS Cloud | General Ledger | General Ledger Is <xxxx> period open for general ledger? Cost center Owner 2. Who is the cost center owner of cost center <xxxx>? 3. Who is the manager of cost center Onwer? | 3

## Slide 6: Timeline
2-Nov | 9-Nov | 16-Nov | 23-Nov | 30-Nov | 7-Dec | 14-Dec | 21-Dec | 28-Dec | 4-Jan | 11-Jan | 18-Jan | 25Jan | 01-Feb
Go-live
Develop high-level technical architecture
Set up Security and SSO for Chat bots
Build integration with Enwisen tool and SaaS application
Review and Finalize use cases
Build WSDL inventory for connecting to Enwisen tool and Oracle
Train the Bots for Enwisen and SaaS
Create dialog flows for Enwisen and SaaS
Conduct unit testing
Develop high-level documentation
Configure Bot for Prod
Migrate intents and flows
Use Cases Finalized
User Testing Complete
Design
Security and Configurations
Chat Bot Development
UAT
Cutover
Christmas Holidays
Hyper Care
Bot development Complete
Conduct User Testing
Train super- users on bot usage
Provide Support

## Slide 7: Resource Plan
Chart: 
Chart: 
Chart: 
Track | Role | Location | Hours
Business Process | PTP Functional | Onshore | 540
Business Process | SCM Functional | Offshore | 585
Business Process | RTR Functional | Offshore | 270
Technology | Developers | Offshore | 1,800
Below is a proposed resource model for Deloitte team.
Track | Role | Location | Hours
Business Process | PTP Functional | Onshore | 540
Business Process | PTP Functional | Offshore | 585
Below is a proposed resource model for FedEx team members. We will work with you to minimize the schedule impact on key stakeholders, testers, etc.

## Slide 8: Effort Estimates and Fees
Chart: 
Chart: 
Work Stream | ~ Hours
Functional (Build, Test and post go-live support) | 1,395
EBS Technical (Build, Test and post go-live support) | 1,800
PMO | 52
Total | ~ 3,300
Our professional fees for this 13 week effort are estimated to be $315K plus expenses (estimated at 15% for those resources required to travel).

## Slide 9: Assumptions
Chart: 
Chart: 
Chatbot may need changes in case any of the Oracle standard process changes
Application level user privileges will restrict the scope and use of the Chatbot
Chatbot will support only English language
Chatbot will support only guided intent, any other utterances will be handled by Chatbot error handling framework
For Genco, Supported modules will be - Order management, Accounts Payables, Accounts Receivables, General Ledger, Self-service Procurement, Inventory Management
Enwisen must provide all the web-services which will fetch all the fields related to tickets
Chatbot will not provide any assistance during application maintenance activities
Deloitte will provide overall project management for the duration of the project
Deloitte & FedEx will coordinate testing activities
Two weeks of post go-live support

## Slide 10: Oracle Chatbot Architecture
Desktop Application, Web Browser, Mobile App Custom Chat Channels
Integration
Oracle Chatbot Platform
Chat Message Platform
Chatbot Engine
Chatbot Component
IBCS
MCS
Context Understanding
Machine Learning
Natural Language Processing
Entity Recognition
Intent Recognition
Dialogue Management
Rule bases/keyword triggering
Q&A Pairs/Scripts
Oracle SaaS Application Cloud, CRM Cloud, Enwisen, Service Desk - Enterprise Applications